## Group member 1
To-do list
To be completed by: |  |  |  | Name: Damian Rozpedowski
Deadline: |  |  |  | Date: 3/24/24
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-03-13 | 2024-03-13 | 2024-03-19 | 6 | Delayed By Midterms. Develop an effective plan, discuss who works on what queries
100% | Preparation | 2024-03-19 | 2024-03-19 |  | 1 | Ensure we have JDBC drivers, and all necessary tools installed to create the project. Had issues with Drivers, had to download MSSQL Driver, we originally tried using MYSQL from the video but this was unnecessary and had problems.
100% | Create 20 SQL Queries, at least 1 from each database. | 2024-03-19 | 2024-03-20 |  | 2 | Create 20 SQL queries using at least 1 from each database.
100% | Create Java file and add in all 20 queries so that they are functional with JDBC MSSQL | 2024-03-21 | 2024-03-21 |  | 1 | Utilize what we know from Project 0 to add in our queries into java and make them functional.
100% | Complete the Java Swing GUI and ensure each query still functions correctly | 2024-03-21 | 2024-03-22 | 2024-03-23 | 3 | Delayed by missing project on BB. Incorporate Java Swing for a GUI.
100% | Create Azure Notebooks file, follow the template, create diagrams, etc. | 2024-03-19 | 2024-03-22 | 2024-03-24 | 6 | GUI took time and delayed by BB, Revise the notebooks ipbyn file to match with the template provided.
100% | Create a PDF of the Azure Notebook file | 2024-03-23 | 2024-03-23 |  | 1 | Use a converter to convert ipbyn file to a pdf, issues finding a good converter.
100% | Record Notebooks Presentation | 2024-03-24 | 2024-03-24 |  | 1 | Create Video Representation
100% | Record JDBC Presentation | 2024-03-24 | 2024-03-24 |  | 1 | Create Video Representation
100% | Record To Do List / Group Presentation | 2024-03-24 | 2024-03-24 |  | 1 | Create Video Representation
100% | Hand-Off | 2024-03-24 | 2024-03-24 |  | 1 | Awaiting completion from all group members. Ensure all files are submitted into google drive and create into VHDX file. Submit.

## Group member 2
To-do list
To be completed by: |  |  |  | Name: Hasnatul Hosna
Deadline: |  |  |  | Date: 3/24/24
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-03-13 | 2024-03-13 | 2024-03-19 | 6 | Delayed By Midterms. Develop an effective plan, discuss who works on what queries
100% | Preparation | 2024-03-19 | 2024-03-19 |  | 1 | Ensure we have JDBC drivers, and all necessary tools installed to create the project. Had issues with Drivers, had to download MSSQL Driver, we originally tried using MYSQL from the video but this was unnecessary and had problems.
100% | Create 20 SQL Queries, at least 1 from each database. | 2024-03-19 | 2024-03-20 |  | 2 | Create 20 SQL queries using at least 1 from each database.
100% | Create Java file and add in all 20 queries so that they are functional with JDBC MSSQL | 2024-03-21 | 2024-03-21 |  | 1 | Utilize what we know from Project 0 to add in our queries into java and make them functional.
100% | Complete the Java Swing GUI and ensure each query still functions correctly | 2024-03-21 | 2024-03-22 | 2024-03-23 | 3 | Delayed by missing project on BB. Incorporate Java Swing for a GUI.
100% | Create Azure Notebooks file, follow the template, create diagrams, etc. | 2024-03-19 | 2024-03-22 | 2024-03-24 | 6 | Revise the notebooks ipbyn file to match with the template provided.
100% | Create a PDF of the Azure Notebook file | 2024-03-23 | 2024-03-23 |  | 1 | Use a converter to convert ipbyn file to a pdf, issues finding a good converter.
100% | Record Notebooks Presentation | 2024-03-24 | 2024-03-24 |  | 1 | Create Video Representation
100% | Record JDBC Presentation | 2024-03-24 | 2024-03-24 |  | 1 | Create Video Representation
100% | Record To Do List / Group Presentation | 2024-03-24 | 2024-03-24 |  | 1 | Create Video Representation
100% | Hand-Off | 2024-03-24 | 2024-03-24 |  | 1 | Awaiting completion from all group members. Ensure all files are submitted into google drive and create into VHDX file. Submit.

## Group member 3
To-do list
To be completed by: |  |  |  | Name: Hannah Kurian
Deadline: |  |  |  | Date: 3/24/24
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-03-13 | 2024-03-13 | 2024-03-19 | 6 | Delayed By Midterms. Develop an effective plan, discuss who works on what queries
100% | Preparation | 2024-03-19 | 2024-03-19 |  | 1 | Ensure we have JDBC drivers, and all necessary tools installed to create the project. Had issues with Drivers, had to download MSSQL Driver, we originally tried using MYSQL from the video but this was unnecessary and had problems.
100% | Create 20 SQL Queries, at least 1 from each database. | 2024-03-19 | 2024-03-20 |  | 2 | Create 20 SQL queries using at least 1 from each database.
100% | Create Java file and add in all 20 queries so that they are functional with JDBC MSSQL | 2024-03-21 | 2024-03-21 |  | 1 | Utilize what we know from Project 0 to add in our queries into java and make them functional.
100% | Complete the Java Swing GUI and ensure each query still functions correctly | 2024-03-21 | 2024-03-22 | 2024-03-23 | 3 | Delayed by missing project on BB. Incorporate Java Swing for a GUI.
100% | Create Azure Notebooks file, follow the template, create diagrams, etc. | 2024-03-19 | 2024-03-22 | 2024-03-24 | 6 | Revise the notebooks ipbyn file to match with the template provided.
100% | Create a PDF of the Azure Notebook file | 2024-03-23 | 2024-03-23 |  | 1 | Use a converter to convert ipbyn file to a pdf, issues finding a good converter.
100% | Record Notebooks Presentation | 2024-03-24 | 2024-03-24 |  | 1 | Create Video Representation
100% | Record JDBC Presentation | 2024-03-24 | 2024-03-24 |  | 1 | Create Video Representation
100% | Record To Do List / Group Presentation | 2024-03-24 | 2024-03-24 |  | 1 | Create Video Representation
100% | Hand-Off | 2024-03-24 | 2024-03-24 |  | 1 | Awaiting completion from all group members. Ensure all files are submitted into google drive and create into VHDX file. Submit.

## Group member 4
To-do list
To be completed by: |  |  |  | Name: Essmer Sanchez
Deadline: |  |  |  | Date: 3/24/24
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-03-13 | 2024-03-19 | 2024-03-19 | 6 | Delayed By Midterms. Develop an effective plan, discuss who works on what queries
100% | Preparation | 2024-03-19 | 2024-03-19 |  | 1 | Ensure we have JDBC drivers, and all necessary tools installed to create the project. Had issues with Drivers, had to download MSSQL Driver, we originally tried using MYSQL from the video but this was unnecessary and had problems.
100% | Create 20 SQL Queries, at least 1 from each database. | 2024-03-19 | 2024-03-20 |  | 2 | Create 20 SQL queries using at least 1 from each database.
100% | Create Java file and add in all 20 queries so that they are functional with JDBC MSSQL | 2024-03-21 | 2024-03-21 |  | 1 | Utilize what we know from Project 0 to add in our queries into java and make them functional.
100% | Complete the Java Swing GUI and ensure each query still functions correctly | 2024-03-21 | 2024-03-22 | 2024-03-23 | 3 | Delayed by missing project on BB. Incorporate Java Swing for a GUI.
100% | Create Azure Notebooks file, follow the template, create diagrams, etc. | 2024-03-19 | 2024-03-22 | 2024-03-24 | 6 | Revise the notebooks ipbyn file to match with the template provided.
100% | Create a PDF of the Azure Notebook file | 2024-03-23 | 2024-03-23 |  | 1 | Use a converter to convert ipbyn file to a pdf, issues finding a good converter.
100% | Record Notebooks Presentation | 2024-03-24 | 2024-03-24 |  | 1 | Create Video Representation
100% | Record JDBC Presentation | 2024-03-24 | 2024-03-24 |  | 1 | Create Video Representation
100% | Record To Do List / Group Presentation | 2024-03-24 | 2024-03-24 |  | 1 | Create Video Representation
100% | Hand-Off | 2024-03-24 | 2024-03-24 |  | 1 | Awaiting completion from all group members. Ensure all files are submitted into google drive and create into VHDX file. Submit.

## Group member 5
To-do list
To be completed by: |  |  |  | Name: Zicheng Yang
Deadline: |  |  |  | Date: 3/24/24
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-03-13 | 2024-03-13 | 2024-03-19 | 6 | Delayed By Midterms. Develop an effective plan, discuss who works on what queries
100% | Preparation | 2024-03-19 | 2024-03-19 |  | 1 | Ensure we have JDBC drivers, and all necessary tools installed to create the project. Had issues with Drivers, had to download MSSQL Driver, we originally tried using MYSQL from the video but this was unnecessary and had problems.
100% | Create 20 SQL Queries, at least 1 from each database. | 2024-03-20 | 2024-03-20 | 2024-03-24 | 5 | Create 20 SQL queries using at least 1 from each database.
?% | Create Java file and add in all 20 queries so that they are functional with JDBC MSSQL | 2024-03-21 | 2024-03-21 | 2024-03-24 | 4 | Issues with Java Drivers. We tried to help him but not getting responses.
?% | Complete the Java Swing GUI and ensure each query still functions correctly | 2024-03-21 | 2024-03-22 | 2024-03-24 | 4 | Issues with Java Drivers. We tried to help him but not getting responses.
?% | Create Azure Notebooks file, follow the template, create diagrams, etc. | 2024-03-19 | 2024-03-22 | 2024-03-24 | 6 | We do not know, very little contact with Zicheng.
?% | Create a PDF of the Azure Notebook file | 2024-03-23 | 2024-03-23 | 2024-03-24 | 2 | We do not know, very little contact with Zicheng.
?% | Record Notebooks Presentation | 2024-03-24 | 2024-03-24 | 2024-03-24 | 1 | We do not know, very little contact with Zicheng.
?% | Record JDBC Presentation | 2024-03-24 | 2024-03-24 |  | 1 | We do not know, very little contact with Zicheng.
?% | Record To Do List / Group Presentation | 2024-03-24 | 2024-03-24 |  | 1 | We do not know, very little contact with Zicheng.
?% | Hand-Off | 2024-03-24 | 2024-03-24 |  | 1 | We do not know, very little contact with Zicheng.