## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  | % Complete | Actual (beyond plan) | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Project Planning | 1 | 6 | 1 | 4 | 100% | bar: PERIODS 1; PERIODS 6 to PERIODS 9
Preparation | 6 | 1 | 6 | 2 | 100% | bar: PERIODS 6 to PERIODS 7
Damian's 20 Queries | 2 | 4 | 2 | 5 | 100% | bar: PERIODS 7 to PERIODS 8
Damian's Java File | 4 | 8 | 4 | 6 | 100% | bar: PERIODS 8 to PERIODS 9
Damian's Swing | 4 | 2 | 4 | 8 | 100% | bar: PERIODS 9 to PERIODS 11
Damian's Azure Notebook File | 4 | 3 | 4 | 6 | 100% | bar: PERIODS 7; PERIODS 10 to PERIODS 12
Damian's PDF Conversion | 5 | 4 | 5 | 3 | 100% | bar: PERIODS 10 to PERIODS 11
Damian's Recording Notebooks | 5 | 2 | 5 | 5 | 100% | bar: PERIODS 10
Damian's Recording JDBC | 5 | 2 | 5 | 6 | 100%
Damian's Recording (To Do List) | 6 | 5 | 6 | 7 | 100%
Damian's Handoff | 6 | 1 | 5 | 8 | 100%
Hasnatul's 20 Queries | 9 | 3 | 9 | 3 | 100% | bar: PERIODS 7 to PERIODS 8
Hasnatul's Java File | 9 | 6 | 9 | 7 | 100% | bar: PERIODS 6 to PERIODS 7
Hasnatul's Swing | 9 | 3 | 9 | 1 | 100% | bar: PERIODS 9 to PERIODS 11
Hasnatul's Azure Notebook File | 9 | 4 | 8 | 5 | 100% | bar: PERIODS 7; PERIODS 10 to PERIODS 12
Hasnatul's PDF Conversion | 10 | 5 | 10 | 3 | 100% | bar: PERIODS 10 to PERIODS 11
Hasnatul's Recording Notebooks | 11 | 2 | 11 | 5 | 100% | bar: PERIODS 10
Hasnatul's Recording JDBC | 12 | 6 | 12 | 7 | 100%
Hasnatul's Recording (To Do List) | 12 | 1 | 12 | 5 | 100%
Hasnatul's Handoff | 14 | 5 | 14 | 6 | 100%
Hannah's 20 Queries | 14 | 8 | 14 | 2 | 100% | bar: PERIODS 7 to PERIODS 8
Hannah's Java File | 14 | 7 | 14 | 3 | 100% | bar: PERIODS 6 to PERIODS 7
Hannah's Swing | 15 | 4 | 15 | 8 | 100% | bar: PERIODS 9 to PERIODS 11
Hannah's Azure Notebook File | 15 | 5 | 15 | 3 | 100% | bar: PERIODS 7; PERIODS 10 to PERIODS 12
Hannah's PDF Conversion | 15 | 8 | 15 | 5 | 100% | bar: PERIODS 10 to PERIODS 11
Hannah's Recording Notebooks | 16 | 28 | 16 | 30 | 100% | bar: PERIODS 10
Hannah's Recording JDBC | 14 | 8 | 14 | 2 | 100%
Hannah's Recording (To Do List) | 14 | 7 | 14 | 3 | 100%
Essmers's 20 Queries | 15 | 4 | 15 | 8 | 100% | bar: PERIODS 7 to PERIODS 8
Essmers's Java File | 15 | 5 | 15 | 3 | 100% | bar: PERIODS 6 to PERIODS 7
Essmers's Swing | 15 | 8 | 15 | 5 | 100% | bar: PERIODS 9 to PERIODS 11
Essmers's Azure Notebook File | 16 | 28 | 16 | 30 | 100% | bar: PERIODS 7; PERIODS 10 to PERIODS 12
Essmers's PDF Conversion | 14 | 8 | 14 | 2 | 100% | bar: PERIODS 10 to PERIODS 11
Essmers's Recording Notebooks | 14 | 7 | 14 | 3 | 100% | bar: PERIODS 10
Essmers's Recording JDBC | 15 | 4 | 15 | 8 | 100%
Essmers's Recording (To Do List) | 15 | 5 | 15 | 3 | 100%
Zicheng's 20 Queries | 15 | 8 | 15 | 5 | 100% | bar: PERIODS 7 to PERIODS 12
Zicheng's Java File | 16 | 28 | 16 | 30 | 100% | bar: PERIODS 6 to PERIODS 12
Zicheng's Swing | 14 | 8 | 14 | 2 | 100% | bar: PERIODS 9 to PERIODS 12
Zicheng's Azure Notebook File | 14 | 7 | 14 | 3 | 100% | bar: PERIODS 7; PERIODS 10 to PERIODS 12
Zicheng's PDF Conversion | 15 | 4 | 15 | 8 | 100% | bar: PERIODS 10 to PERIODS 12
Zicheng's Recording Notebooks | 15 | 5 | 15 | 3 | 100% | bar: PERIODS 10
Zicheng's Recording JDBC | 15 | 8 | 15 | 5 | 100%
Zicheng's Recording (To Do List) | 16 | 28 | 16 | 30 | 100%