## Project Planner
Project Planner
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: 10 | 10 |  |  | Plan Duration | [5 empty] | Actual Start | % Complete | Actual (beyond plan) | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
| Downloading and setting up the environment | 1 | 2 | 1 | 2 | 100% | bar: PERIODS 1 to PERIODS 5
| Meeting with group to discuss the requirements | 1 | 2 | 1 | 2 | 100%
| Completion of stored procedures | 3 | 6 | 3 | 6 | 100% | bar: PERIODS 3 to PERIODS 8
| Completion of sequence objects | 3 | 3 | 3 | 3 | 100% | bar: PERIODS 3 to PERIODS 8
| Completion of views | 7 | 8 | 7 | 8 | 100% | bar: PERIODS 7 to PERIODS 9
| JDBC implementation | 7 | 1 | 7 | 1 | 85% | bar: PERIODS 7 to PERIODS 10
| Member 1 video | 9 | 1 | 9 | 1 | 50%
| Member 2 video | 9 | 1 | 9 | 1 | 60%
| Member 3 video | 9 | 1 | 9 | 1 | 75%
| Member 4 video | 9 | 1 | 9 | 1 | 100%
| Member 1 JDBC video | 9 | 1 | 9 | 1 | 60%
| Member 2 JDBC video | 9 | 1 | 9 | 1 | 0%
| Member 3 JDBC video | 9 | 1 | 9 | 1 | 50%
| Member 4 JDBC video | 9 | 1 | 9 | 1 | 0%