## Group member 1
To-do list
To be completed by: |  |  |  | Name: Damian Rozpedowski
Deadline: |  |  |  | Date: 04/14/2024
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-04-03 | 2024-04-03 | 2024-04-04 | 1 | Talked with group members regarding the project
100% | Downloading, setting up the environment | 2024-04-03 | 2024-04-03 | 2024-04-04 | 1 | Clarified any downloading, technical questions
100% | Completion of stored procedures | 2024-04-06 | 2024-04-08 | 2024-04-13 | 5 | completed the stored procedures for all tables
100% | Completion of sequence objects | 2024-04-06 | 2024-04-08 | 2024-04-08 | 2 | completed the sequence objects
100% | Completion of views | 2024-04-11 | 2024-04-13 | 2024-04-13 | 2 | Completed the view tables for all given tables
100% | JDBC Implementation | 2024-04-13 | 2024-04-14 | 2024-04-14 | 1 | Converted SQL code to Java.
100% | SQL video | 2024-04-13 | 2024-04-14 | 2024-04-14 | 1 | Recorded video for SQL code
100% | JDBC video | 2024-04-13 | 2024-04-14 | 2024-04-14 | 1 | Recorded video of java implementation
100% | Follow-up | 2024-04-13 | 2024-04-14 | 2024-04-14 | 1 | Asked any clarification question/finishing the project

## Group member 2
To-do list
To be completed by: |  |  |  | Name: Essmer Sanchez
Deadline: |  |  |  | Date: 04/14/2024
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-04-03 | 2024-04-03 | 2024-04-04 | 1 | Talked with group members regarding the project
100% | Downloading, setting up the environment | 2024-04-03 | 2024-04-03 | 2024-04-04 | 1 | Clarified any downloading, technical questions
100% | Completion of stored procedures | 2024-04-06 | 2024-04-08 | 2024-04-13 | 5 | completed the stored procedures for all tables
100% | Completion of sequence objects | 2024-04-06 | 2024-04-08 | 2024-04-08 | 2 | completed the sequence objects
100% | Completion of views | 2024-04-11 | 2024-04-13 | 2024-04-13 | 2 | Completed the view tables for all given tables
100% | JDBC Implementation | 2024-04-13 | 2024-04-14 | 2024-04-14 | 1 | Converted SQL code to Java.
100% | SQL video | 2024-04-13 | 2024-04-14 | 2024-04-14 | 1 | Recorded video for SQL code
100% | JDBC video | 2024-04-13 | 2024-04-14 | 2024-04-14 | 1 | Recorded video of java implementation
100% | Follow-up | 2024-04-13 | 2024-04-14 | 2024-04-14 | 1 | Asked any clarification question/finishing the project

## Group member 3
To-do list
To be completed by: |  |  |  | Name: Hasnatul Hosna
Deadline: |  |  |  | Date: 04/14/2024
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-04-03 | 2024-04-03 | 2024-04-04 | 1 | Talked with group members regarding the project
100% | Downloading, setting up the environment | 2024-04-03 | 2024-04-03 | 2024-04-04 | 1 | Clarified any downloading, technical questions
100% | Completion of stored procedures | 2024-04-06 | 2024-04-08 | 2024-04-13 | 5 | completed the stored procedures for all tables
100% | Completion of sequence objects | 2024-04-06 | 2024-04-08 | 2024-04-08 | 2 | completed the sequence objects
100% | Completion of views | 2024-04-11 | 2024-04-13 | 2024-04-13 | 2 | Completed the view tables for all given tables
100% | JDBC Implementation | 2024-04-13 | 2024-04-14 | 2024-04-14 | 1 | Converted SQL code to Java.
100% | SQL video | 2024-04-13 | 2024-04-14 | 2024-04-14 | 1 | Recorded video for SQL code
100% | JDBC video | 2024-04-13 | 2024-04-14 | 2024-04-14 | 1 | Recorded video of java implementation
100% | Follow-up | 2024-04-13 | 2024-04-14 | 2024-04-14 | 1 | Asked any clarification question/finishing the project

## Group member 4
To-do list
To be completed by: |  |  |  | Name: Hannah Kurian
Deadline: |  |  |  | Date: 04/14/2024
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2024-04-03 | 2024-04-03 | 2024-04-04 | 1 | Talked with group members regarding the project
100% | Downloading, setting up the environment | 2024-04-03 | 2024-04-03 | 2024-04-04 | 1 | Clarified any downloading, technical questions
100% | Completion of stored procedures | 2024-04-06 | 2024-04-08 | 2024-04-13 | 5 | completed the stored procedures for all tables
100% | Completion of sequence objects | 2024-04-06 | 2024-04-08 | 2024-04-08 | 2 | completed the sequence objects
100% | Completion of views | 2024-04-11 | 2024-04-13 | 2024-04-13 | 2 | Completed the view tables for all given tables
100% | JDBC Implementation | 2024-04-13 | 2024-04-14 | 2024-04-14 | 1 | Converted SQL code to Java.
100% | SQL video | 2024-04-13 | 2024-04-14 | 2024-04-14 | 1 | Recorded video for SQL code
100% | JDBC video | 2024-04-13 | 2024-04-14 | 2024-04-14 | 1 | Recorded video of java implementation
100% | Follow-up | 2024-04-13 | 2024-04-14 | 2024-04-14 | 1 | Asked any clarification question/finishing the project