## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: 7 | 1 |  |  | Plan Duration | [5 empty] | Actual Start | % Complete | Actual (beyond plan) | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Table Creation | 1 | 3 | 1 | 2 | 100% | bar: PERIODS 1 to PERIODS 2
Stored Procedures | 2 | 5 | 2 | 6 | 100% | bar: PERIODS 2 to PERIODS 6
Creation of User defined data type | 1 | 3 | 1 | 2 | 100% | bar: PERIODS 1 to PERIODS 2
JDBC implementation | 6 | 7 | 6 | 7 | 100%
Member 1 queries | 6 | 7 | 6 | 7 | 100%
Member 2 queries | 6 | 7 | 6 | 7 | 100%
Member 3 queries | 6 | 7 | 6 | 7 | 100%
Member 4 queries | 6 | 7 | 6 | 7 | 100%
Member 1 table creation | 1 | 3 | 1 | 2 | 100% | bar: PERIODS 1 to PERIODS 2
Member 2 table creation | 1 | 3 | 1 | 2 | 100% | bar: PERIODS 1 to PERIODS 2
Member 3 table creation | 1 | 3 | 1 | 2 | 100% | bar: PERIODS 1 to PERIODS 2
Member 4 table creation | 1 | 3 | 1 | 2 | 100% | bar: PERIODS 1 to PERIODS 2
Member 1 presentation | 6 | 7 | 6 | 7 | 100%
Member 2 presentation | 6 | 7 | 6 | 7 | 100%
Member 3 presentation | 6 | 7 | 6 | 7 | 100%
Member 4 presentation | 6 | 7 | 6 | 7 | 100%